Roof-Aid CRM

Tier 1 Implementation Project Plan

Version 1.1  |  Updated April 2, 2026  |  10-Week Delivery

# 1. Executive Summary

What you will receive at the end of 10 weeks:

- A complete, production-ready multi-tenant SaaS CRM tailored for roofing companies.

- Web application (Next.js) + native mobile app (Flutter) for field inspectors (Rufero).

- All core features: prospect pipeline, human softphone (Telnyx), SMS/email, appointments, documents & e-signature, supplement admin panel, basic analytics, onboarding checklist, and billing.

- Automated tenant provisioning with full multi-tenant security via Supabase Row Level Security.

- Ready for immediate pilot customers and first revenue.

- Higher tiers (Storm Leads, AI Calling, Computer Vision) will be added in future sprints.

| Start Date | Go-Live Target (Web + Mobile) | Total Duration |
| --- | --- | --- |
| April 3, 2026 | End of Week 10 | 10 Weeks |

# 2. Project Objectives & Success Criteria

## Objectives

- Deliver a stable, secure, and user-friendly Tier 1 CRM that roofing companies can start using immediately.

- Build with a clean, scalable architecture (Repository + Adapter pattern) so future tiers can be added without rework.

- Meet or exceed the performance and security standards defined in the original specification.

## Success Criteria (Definition of Done)

- All 9 milestones completed and signed off.

- Full end-to-end workflow tested: lead import → call → appointment → inspection → signed contract.

- Multi-tenant isolation verified — no cross-tenant data access possible.

- Mobile app works offline, passes basic App Store / Play Store checks.

- Automated tenant provisioning works.

- A 14-day free trial is fully functional with Stripe.

# 3. Technology Stack

| Layer | Technology | Reason |
| --- | --- | --- |
| Web Frontend | Next.js 15 (App Router + TypeScript + Tailwind) | Modern, fast, excellent PWA support |
| Backend / DB | Supabase (PostgreSQL + RLS + Edge Functions + Realtime) | Scalable, secure multi-tenancy, real-time updates |
| Mobile App | Flutter (single codebase) | Native iOS & Android performance + offline support |
| Telephony | Telnyx (WebRTC + SMS) | As specified |
| Email | SendGrid | Personal sender per agent |
| Payments | Stripe | Subscriptions + future commissions |
| Maps | Google Maps | As specified |
| PDF Generation | pdf-lib (in Edge Functions) | Professional contracts |

# 4. Detailed Milestone Plan (10 Weeks)

The plan has been extended from 8 to 10 weeks. The additional time is distributed across the Foundation phase (M1 now spans Weeks 1–2) and the final QA/Launch phase (M8 now spans Weeks 9–10). All other milestones retain one dedicated week each, with 10% buffer built into every week.

| M# | Period | Focus | Done When (Client Acceptance Criteria) |
| --- | --- | --- | --- |
| M1 | Weeks 1–2(Days 1–5) | Foundation & Multi-Tenant Core | Monorepo ready, Supabase live, Next.js + Flutter run locally. All tables + RLS policies complete. Tenant provisioning works. All secrets configured. |
| M2 | Weeks 2–3 | Prospect Pipeline + Dashboard | Web dashboard with a 60-record Anti-Collision list. Mobile basic prospect list. Real-time updates. |
| M3 | Week 4 | Dashboard Polish + Maps | Full dashboard, Google Maps, proximity search, prospect profile tabs. Mobile map view functional. |
| M4 | Week 5 | Communication (Phone/SMS/Email) | Telnyx softphone is working, SMS inbox, SendGrid emails, and DNC compliance. Mobile SMS reply. |
| M5 | Week 6 | Appointments + Documents & E-Signature | Calendar, appointment flow, PDF contracts, e-signature. Mobile: full Inspection screen (camera + signature + offline). |
| M6 | Week 7 | Mobile Deep Dive + Offline | Mobile offline mode, photo upload, document viewer, push notifications fully working. |
| M7 | Week 8 | Admin, Analytics & Onboarding | Admin panel, CSV import, basic analytics, and onboarding checklist. Mobile settings polished. |
| M8 | Weeks 9 | Billing & Security | Stripe trial/subscription, security audit. |
| M9 | Week 10 | QA & Launch | Full end-to-end testing, deployment to production staging, and Go-live ready. |

# 5. Weekly Rhythm

- Monday: Planning & task breakdown.

- Tuesday–Thursday: Focused development.

- Friday: Milestone sign-off — short meeting to review deliverables

- 10% buffer time is built into each week for unexpected issues.

# 6. What Is Included in Tier 1 (Scope)

- Prospect pipeline & dashboard (with Anti-Collision System)

- Human softphone (Telnyx), SMS, Email

- Appointments & scheduling

- Documents & e-signature (3 contract types)

- Rufero mobile app with offline support

- Admin panel + basic analytics

- Onboarding checklist + self-service features

- Stripe billing (Tier 1 subscription + 14-day trial)

- Full multi-tenant security & tenant provisioning

- PWA support on the web

# 7. Assumptions & Dependencies

- You will provide timely feedback on weekly demos.

- All third-party API keys (Telnyx, SendGrid, Stripe, Google Maps) will be provided before Week 1 ends.

- Final design decisions (colors, logo, minor UI tweaks) can be handled during development.